## Sheet1
Completion Check | Process | Tcode / Table / Excel | Provider | Executor | Validator | When (HK) | When (US) | Time
| Set user security |  | Rahul Attarde | Michael Webb | Rahul Attarde |  | 2013-03-25
| Move transports for Warehouse |  | Babu Lankipalli | Michael Webb | Babu Lankipalli |  | 2013-04-01
| SAP WM transports |  | Babu Lankipalli | Michael Webb | Babu Lankipalli
| Putaway / Picking forms |  | Babu Lankipalli | Michael Webb | Babu Lankipalli
| LSMW for material extension |  | Babu Lankipalli | Michael Webb | Babu Lankipalli
| LSMWs for inventory conversion |  | Babu Lankipalli | Michael Webb | Babu Lankipalli
| LSMW for Chainlink IDOCs |  | Babu Lankipalli | Michael Webb | Dan Brennan
| Material creation program changes |  | Babu Lankipalli | Michael Webb | Babu Lankipalli
| Create Storage Bins | Winshuttle | Horace Ng | Babu Lankipalli | Rahul Attarde | 2013-04-02 | 2013-04-01
| Prepare file with storage bin names |  | Horace Ng | Babu Lankipalli | Rahul Attarde | 2013-03-26
| Verify storage bin upload file |  | Horace Ng | Babu Lankipalli | Rahul Attarde | 2013-03-26
| Verify Storage Bins (Audit in excel) | LS11 | Babu Lankipalli | Rahul Attarde | Horace Ng | 2013-04-02 | 2013-04-01
| Download newly created storage bins from SAP | Excel | Rahul Attarde | Rahul Attarde | Horace Ng | 2013-04-02
| Vlookup and audit SIMS and SAP storage bins | Excel | Rahul Attarde | Rahul Attarde | Horace Ng | 2013-04-02
| Download all material numbers HK / KR materials | Table MARC | Babu Lankipalli | Laxman (BMS) | Doug Snyder |  | 2013-03-27
| Identify and download materials with Inventory in SAP (Priority 1) | MB52 | Babu Lankipalli | Laxman (BMS) | Doug Snyder |  | 2013-03-27
| Identify and download materials with open POs in SAP (Priority 1) | ME2N | Babu Lankipalli | Laxman (BMS) | Doug Snyder |  | 2013-03-27
| Combine Priority 1 materials and prepare single list | Excel | Babu Lankipalli | Laxman (BMS) | Doug Snyder |  | 2013-03-27
| Download all materials excluding Priority 1 (these will be Priority 2) | MARC | Babu Lankipalli | Laxman (BMS) | Doug Snyder |  | 2013-03-28
| Prepare file to extend materials with Priority 1 | Excel | Laxman (BMS) | Durga Prasad (BMS) | Babu Lankipalli |  | 2013-03-28
| Prepare file to extend materials with Priority 2 | Excel | Laxman (BMS) | Durga Prasad (BMS) | Babu Lankipalli |  | 2013-03-28
| Extend all identified materials for HK and KR | MM01 | Laxman (BMS) | Durga Prasad (BMS) | Doug Snyder |  | 4/2/2013 - 4/5/2013
| Extend all identified materials with Priority 1 | MM01 | Laxman (BMS) | Durga Prasad (BMS) | Doug Snyder |  | 2013-04-02
| Extend all identified materials with Priority 2 | MM01 | Laxman (BMS) | Durga Prasad (BMS) | Doug Snyder |  | 2013-04-03
| Download all materials extended to warehouse HKW | Table MLGN | Laxman (BMS) | Durga Prasad (BMS) | Babu Lankipalli |  | 2013-04-05
| Compare pre-load materials and MLGN materials (Priority 1) |  | Babu Lankipalli | Babu Lankipalli | Doug Snyder |  | 2013-04-03
| Compare pre-load materials and MLGN materials (Priority 2) |  | Babu Lankipalli | Babu Lankipalli | Doug Snyder |  | 2013-04-05
| Audit report with pre and post extension count | Excel | Babu Lankipalli | Babu Lankipalli | Doug Snyder |  | 2013-04-05
| Modify Allocation run job - remove variant for plants HK / KR | SM37 (NA_SD_ARUN) | Dan Brennan | Michael Webb | Dan Brennan |  | 2013-04-03 | 15:00
| Modify delivery creation job - remove variant HK / KR | SM37 (NA_SD_DELV_CREATE) | Dan Brennan | Michael Webb | Dan Brennan |  | 2013-04-03 | 15:00
| Identify all open deliveries | VL06O | Dan Brennan | Dan Brennan | Ashley Parker |  | 2013-04-03
| Download all open deliveries with sales order reference in Excel | Excel | Dan Brennan | Dan Brennan | Ashley Parker |  | 2013-04-03
| Delete all open deliveries | LSMW | Dan Brennan | Ashley Parker | Dan Brennan |  | 2013-04-04
| De-allocate stock from sales orders in SAP | J4AB | Dan Brennan | Ashley Parker | Dan Brennan |  | 2013-04-04
| Verify if any stock is still allocated in SAP |  | Dan Brennan |  | Dan Brennan |  | 2013-04-04
| De-allocate stock in SIMS | SIMS | Horace Ng | Horace Ng | Kris Paxson |  | 4/4/2013 - 4/5/2013
| Identify all open POs for plants 0510 / 0580 | ME2N | Babu Lankipalli | Laxman (BMS) | Andrew Ingham |  | 2013-04-04
| Download all open POs | Excel | Babu Lankipalli | Laxman (BMS) | Andrew Ingham |  | 2013-04-04
| Mass update all open POs storage locations | MEMASSPO | Laxman (BMS) | Babu Lankipalli | Andrew Ingham |  | 2013-04-05
| Verify all open POs | ME2N | Babu Lankipalli | Babu Lankipalli | Andrew Ingham |  | 2013-04-05
| Create inventory file with quantity and location reference | SIMS / Excel | Horace Ng | Horace Ng | Rahul Attarde | 2013-04-05
| Download SAP inventory in Excel for audit | MB52 | Rahul Attarde | Jen Wolf | Kris Paxson | 2013-04-05
| Prepare inventory conversion file for upload | Excel | Rahul Attarde | Rahul Attarde | Jen Wolf | 2013-04-05
| Execute LSMW for inventory conversion | LSMW | Rahul Attarde | Durga Prasah (BMS) | Rahul Attarde | 4/5/2013 - 4/6/2013
| Download post conversion inventory in Excel for audit | MB52 | Rahul Attarde | Rahul Attarde | Jen Wolf | 2013-04-06
| Compare (Vlookup) pre and post inventory | Excel | Rahul Attarde | Rahul Attarde | Jen Wolf | 2013-04-06
| Compare SIMS and Post inventory for location reference | Excel | Rahul Attarde | Rahul Attarde | Jen Wolf | 2013-04-06
| Communicate any inventory differences |  | Rahul Attarde | Rahul Attarde | Jen Wolf | 2013-04-07
| Reconcile inventory differences - (561 / 562 movements) | Winshuttle | Rahul Attarde | Jen Wolf | Jen Wolf | 2013-04-07
| Modify Allocation run job - add variant for plants HK / KR | SM37 (NA_SD_ARUN) | Dan Brennan | Dan Brennan | Dan Brennan |  | 2013-04-07 | 7:00
| Modify delivery creation job - add variant for plants HK / DR | SM37 (NA_SD_DELV_CREATE) | Dan Brennan | Dan Brennan | Dan Brennan |  | 2013-04-07 | 7:00
| Execute allocation run job | SM37 (NA_SD_ARUN) | Dan Brennan | Dan Brennan | Maple Lam |  | 2013-04-07
| Execute delivery creation job | SM37 (NA_SD_DELV_CREATE) | Dan Brennan | Dan Brennan | Maple Lam |  | 2013-04-07
| Print new delivery outputs | (Automatic) | Dan Brennan | Dan Brennan | Horace Ng |  | 2013-04-07
| Monitor daily reconciliation reports | [5 empty] | 2013-04-08