## Sheet1
Seq | Function | Task Description | Dependency | Evironment | Tcode/Program | Asignee | Estimate Effort in hours | Details/Commnets
10 | Communication | Send out internal communication to the departments may be impacted regarding the new SNC vendor on-boarding | N/A | Email |  | Tom | 0.5
20 | Education | Training Session with Vendor and HK team | N/A | Email/Web |  | Tom | 2
30 | Business Readiness | Determine whether a new Vendor ID is needed or which vendor ID to use for post-SNC go live | N/A | NEP |  | Tom/Robin
40 | Business Readiness | Add vendor ID to MCP | 30 | MCP |  | Bibin/Babu | 0.25
50 | Business Readiness | Info Record conversion for the vendor | 30 | NEP | LSMW - ZSNC_PIR | Babu | 40~80
60 | PO Push | Setup the condition records in ECC to trigger ZSNC output type. | 30 | NEP | NACE > EF > ZSNC | Bhumi | 0.25 | Add to the 2nd access sequence for NB and Z3NB
70 | PO Push | Check the crystal report if it is generating the input file for the customer Master Data transfer (CIM) by vendor, if so we may have to add the new vendor. | N/A | BOBJ | BI>Datasource>GSIC>GSCI009 | Bhumi | 0.25 | Normally, no action is needed as the report is not vendor specific
80 | PO Push | Check the crystal report if it is generating the input file for the material master Data transfer (SIM) by vendor, if so we may have to add the new vendor. | N/A | BOBJ | BI>Datasource>SNC>SNC Report 1 | Bhumi | 0.25 | Normally, no action is needed as the report is not vendor specific
90 | PO Push | Update Variant to include new vendor ID in PO Push | 30 | NEP | SM37>ZSNC_PO_PUSH or SA38>RM06ENDR_ALV | Bhumi
100 | PO Push | CIF the Vendor master (Vendor master data transfer). | N/A | NEP & SNC | CFM1 & CFM2 | Bhumi/Adithya | 0.25
110 | PO Push | Create the Transportation lane combination with all the plants which we would think we may send the POs | N/A | SNP | /SAPAPO/SCC_TL1 | Bhumi/Adithya | 4
120 | ECC-SNC integration | Check of the phase master would be working fine for the new vendor. | N/A | SNP | SM37>ZPHASE_MASTER | Bhumi | 0.25
130 | ECC-SNC integration | Update Work Order Creation Job with proper Variant | N/A | SNP | SM37>ZSNC_WORKORDERS | Bhumi | 0.5
140 | ECC-SNC integration | Schedule ASN job in SNC to include new vendor | N/A | SNP | SM37>ZASN_FORWARD | Bhumi
150 | Basic Config | Create Preliminary PO in SNC before creating number range for WO and ASN | N/A | NEP & SNC | ME21N
160 | Basic Config | Create number ranges for the Work Order creation. | 150 | SNC Web Portal | Web Portal
170 | Basic Config | Create number ranges for ASN. | 150 | SNC Web Portal | Web Portal
180 | Security | Create SAP ID for Factrory users | N/A | SNP | SU01 | Infrastructure/Basis
190 | Security | Assign the required user ids to this vendor in BP transaction | 180 | SNP | BP | Bhumi
200 | Security | Access to BI SNC folder for report SNC100~SNC190 | 180 | BOBJ |  | Infrastructure/BI Team
210 | Day End Process/Security | Create Windows AD user IDs for Factory users | N/A | Windows |  | Infrastructure
220 | Day End Process/Security | Assign user IDs to vendor number for Factory users in .NET | 180 | Windows |  | Infrastructure
230 | Day End Process/Security | Create a unique user id for File Tranfer download/upload process - Day end process. Copy roles from ID EBVEND | N/A | SNP |  | Bhumi with Basis/Inf
240 | Day End Process | Create the upload profile using the desginated vendor ID | 230 | SNC Web Portal | Web Portal
250 | Day End Process | Create the download profile using the designated vendor ID | 230 | SNC Web Portal | Web Portal
260 | Day End Process | Schedule the download job. Copying ZFTRD_ML | N/A | SNP | SM37> copy ZFTRD_ML and use the proper variant for the new vendor along with new time