## OPPM
Project Lead - Surya Basa / Venkat Kondapally | Project: Packing Program | [8 empty] | Resources |  | BMS Hours
Major Tasks | Schedule | [7 empty] | Status | BMS | NEC | Resource | Hours | [7 empty] | Total
Cutover Plan | [8 empty] | l | Surya, Venkat |  | Surya | 4 | 4 | 4 | 4 | 32 | 4 | 4 | 16
PW code handover and review | [8 empty] | ü | Surya, Venkat |  | Venkat | 20 | 20 | 20 | 20 | 20 | 10 | 10 | 10
Test scenarios and results approval | [8 empty] | ü | Surya, Venkat, Siba/Deepak, Prudvi/Karthik, Adithya |  | Siba | 16 | 16 | 16 | 16 | 40 | 24 | 24 | 40
Outbound | [8 empty] | Ù | Surya, Venkat, Siba/Deepak, Prudvi/Karthik |  | Prudvi | 40 | 40 | 40 | 40 | 40 | 40 | 28 | 28
SKU | [9 empty] | Prudvi, Siba/Deepak |  | Adithya | [5 empty] | 8 | 8 | 16
Family - Caselot/Crossdock | [9 empty] | Prudvi, Siba/Deepak |  | Deepak
Mixed | [9 empty] | Prudvi, Siba/Deepak |  | Karthik
Consolidated testing (DEV) | [9 empty] | Surya, Siba/Deepak, Venkat | Dan Brennan
QA Testing (NEC) | [9 empty] | Surya/Deepak, Venkat/Prudvi
Inbound | [9 empty] | Prudvi/Karthik, Adithya, Siba/Deepak
SKU | [9 empty] | Prudvi/Karthik, Adithya, Siba/Deepak
Family | [9 empty] | Prudvi/Karthik, Adithya, Siba/Deepak
Mixed | [9 empty] | Prudvi/Karthik, Adithya, Siba/Deepak
Integration testing (DEV-BMS) | [9 empty] | Surya, Venkat, Siba/Deepak, Adithya
Integration testing (QUA-NEC) | [9 empty] | Surya, Venkat
User Training
Total
Holidays | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 |  | Team - BMS |  |  | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8
Nov - 26 | [9 empty] | Functional | ABAP
Dec - 25 | [9 empty] | Surya Basa | Venkat Kondapally
[10 empty] | Siba Mohapatra | Prudvi Mandadi
[10 empty] | Adithya Vojjal | Karthik Vinayagam
Deepak Yasam
| Nov 20 | Nov 27 | Dec 4 | Dec 11 | Dec 18 | Dec 28 | Jan 4 | Jan 11
Completed | ü
On Schedule | Ù
Behind Schedule | Ú
Hold or Pending | ó
May need attention | l

## Pack by SKU
| Silhouette | Max Box Size - VAS | Pack Type | Test Case | VAS | Pack Type | Alt UOM | Test Data | [6 empty] | Expected Results (BMS) |  |  |  | Pass/Fail | Actual Result | Reason For Failure
S.No |  |  |  |  | MaxBoxSize | By SKU |  | Mat ID | Size | Qty | VAS | PH4 | Run Size | Delivery | Box Series | HU's - Qty | R3 | R4 |  |  | HU2 absent | Alt UoM | Max Size | Run Size | SKU | Family | Unknown/Bug
| One silhouette | No Crossdock, Max Box Size | Pack by SKU |  | Yes | Yes
1 |  |  |  | Single material - Single size | Yes | Yes |  | 10020926 | 638 | 51 | P01, P03 | 016 - 39Thirty |  | 80013679 | B,S | 1-2B-24 1-2B-24 1-1S-3 | Qty <= 3 per box |  | P | 1-2B-24 1-2B-24 1-1S-3
2 |  |  |  | Single material - Single size | Yes | Yes |  | 10020936 | 638 | 62 | P01, P04 | 226 - Porkpie |  | 80013680 | F | 1-3F-18 1-3F-18 1-3F-18 1-2F-8 | Qty <= 6 per box |  | P | 1-3F-18 1-3F-18 1-3F-18 1-2F-8
3 |  |  |  | Single material - Multiple size | Yes | Yes |  | 10020929 | 638 612 658 | 84 51 33 | P01, P17 | 036 - 59Fifty Low Crown |  | 80013682 | A,S | 1-4A-48 1-3A-36 1-4A-48 1-1S-3 1-3A-33 |  |  | P | 1-4A-48 1-3A-36 1-4A-48 1-1S-3 1-3A-33
4 |  |  |  | Multiple material - Multiple size | Yes | Yes |  | 10020928 10021152 | 638 612 658 634 638 612 658 634 | 147 20 39 15 24 22 12 15 | P01, P94 | 032 - 49Forty |  | 80013686 | B,S | 1-12B-144 1-1S-3 1-2B-20 1-4B-39 1-2B-15 1-2B-24 1-2B-22 1-1B-12 1-2B-15 |  |  | P | 1-12B-144 1-1S-3 1-2B-20 1-4B-39 1-2B-15 1-2B-24 1-2B-22 1-1B-12 1-2B-15
5 |  |  |  | Multiple material - Multiple size | Yes | Yes |  | 10020926 10020950 | 638 612 658 638 612 658 | 24 36 75 22 38 49 | P01, P94 | 016 - 39Thirty No PH4 on atleast one material |  | 80013687 | Error # 11(PH4 not maintained for item no .000020 in 0080013687) | NA | Shouldn't pack |  | P | NA
6 |  |  |  | Multiple material - Multiple size | Yes | Yes |  | 10020926 10020950 | 638 612 658 638 612 658 | 200 100 150 60 45 80 | P01, P94 P01,P06 | 016 - 39Thirty No PH4 on atleast one material |  | 80013784 | Error # 11(PH4 not maintained for item no .000020 in 0080013687) | NA | Shouldn't pack |  | P | NA
One silhouette |  | No Crossdock, Max Box Size | Pack by SKU |  | Yes | Yes | Yes
P3 10021177
P2 10021180
P6 10021178
P3+P9 10021184 10021179
P10+P20 10021181 10021182
7 |  |  |  | Single material - Single size | Yes | Yes | Yes | P3 10021177 | 638 | 85 | P01,P07 | 373 - Stretch bucket |  | 80013754 | A | 1-6A-16 1-6A-16 1-6A-16 1-6A-16 1-6A-16 1-2A-5 |  |  | P | 1-6A-16 1-6A-16 1-6A-16 1-6A-16 1-6A-16 1-2A-5
8 |  |  |  | Single material - Single size | Yes | Yes | Yes | P2 10021180 | 638 | 80 | P01,P07 | 383 - Fedora Rolled Brim |  | 80013756 | F | 1-6F-18 1-6F-18 1-6F-18 1-6F-18 1-3F-8 |  |  | P | 1-6F-18 1-6F-18 1-6F-18 1-6F-18 1-3F-8
9 |  |  |  | Single material - Multiple size | Yes | Yes | Yes | P6 10021178 | 638 612 658 | 70 50 90 | P01,P07 | 373 - Stretch bucket |  | 80013757 | A | 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-6 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-2A-2 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-2A-2 |  |  | P | 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-6 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-2A-2 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-6A-8 1-2A-2
10 |  |  |  | Multiple material - Multiple size | Yes | Yes | Yes | P3+P9 10021184 10021179 | 638 612 658 638 612 658 | 25 30 60 60 70 120 | P01,P07 | 373 - Stretch bucket |  | 80013772 | A | 1-6A-16 1-4A-9 1-6A-16 1-6A-14 1-6A-16 1-6A-16 1-6A-16 1-6A-12 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 | Qty =>4 per box |  | P | 1-6A-16 1-4A-9 1-6A-16 1-6A-14 1-6A-16 1-6A-16 1-6A-16 1-6A-12 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5 1-6A-5
11 |  |  |  | Multiple material - Multiple size | Yes | Yes | Yes | P10+P20 10021181 10021182 | 638 612 658 638 612 658 | 50 40 35 20 10 17 | P01, P94 | 384 - Hunting cap |  | 80013780 | A | 1-12A-14 1-12A-14 1-12A-14 1-12A-8 1-12A-14 1-12A-14 1-12A-12 1-12A-14 1-12A-14 1-6A-7 1-12A-7 1-12A-7 1-12A-6 1-12A-7 1-12A-7 1-12A-7 1-12A-7 1-6A-3 |  |  | P | 1-12A-14 1-12A-14 1-12A-14 1-12A-8 1-12A-14 1-12A-14 1-12A-12 1-12A-14 1-12A-14 1-6A-7 1-12A-7 1-12A-7 1-12A-6 1-12A-7 1-12A-7 1-12A-7 1-12A-7 1-6A-3
12 |  |  |  | Multiple material - Multiple size | Yes | Yes | Yes | P10+P20 10021181 10021182 | 638 612 658 638 612 658 | 60 50 30 45 50 30 | P01,P03 P01,P06 | 384 - Hunting cap |  | 80013785 | A | 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-2A-1 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 |  |  | P | 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-2A-1 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2 1-4A-2
One silhouette |  | No Crossdock, No Max Box Size | Pack by SKU |  |  | Yes
13 |  |  |  | Single material - Single size |  | Yes |  | 10020943 | 638 | 82 | P01 | 373 - Stretch bucket |  | 80013701 | A | 1-6A-48 1-6A-34 |  |  | P | 1-6A-48 1-6A-34
14 |  |  |  | Single material - Single size |  | Yes |  | 10020946 | 638 | 121 | P01 | 383 - Fedora Rolled Brim |  | 80013702 | F | 1-6F-36 1-6F-36 1-6F-36 1-3F-13 |  |  | P | 1-6F-36 1-6F-36 1-6F-36 1-3F-13
15 |  |  |  | Single material - Multiple size |  | Yes |  | 10020944 | 638 612 658 | 70 60 50 | P01 | 373 - Stretch bucket |  | 80013703 | A,S | 1-6A-48 1-3A-22 1-6A-48 1-2A-12 1-6A-48 1-1S-2 |  |  | P | 1-6A-48 1-3A-22 1-6A-48 1-2A-12 1-6A-48 1-1S-2
16 |  |  |  | Multiple material - Multiple size |  | Yes |  | 10020943 10020946 | 638 612 658 638 612 658 | 65 75 22 46 85 100 | P01 | 373 - Stretch bucket |  | 80013752 | A | 1-6A-48 1-6A-44 1-6A-48 1-3A-17 1-6A-45 1-6A-48 1-1A-7 1-6A-48 1-3A-19 1-6A-48 |  |  | P | 1-6A-48 1-6A-44 1-6A-48 1-3A-17 1-6A-45 1-6A-48 1-1A-7 1-6A-48 1-3A-19 1-6A-48
17 |  |  |  | Multiple material - Multiple size |  | Yes |  | 10020947 10020948 | 638 612 658 638 612 658 | 92 65 45 55 67 48 | P01, P02 | 384 - Hunting cap |  | 80013706 | Error # 1 (Packing not possible due to multiple VAS codes.) | NA |  |  | P | NA
One silhouette |  | No Crossdock, No Max Box Size | Pack by SKU |  |  | Yes | Yes
10020927 10020929
10020932 10020933 10020934
P10+P2 10021173 10021186
P2+P20 10021186 10021174
18 |  |  |  | Single material - Single size |  | Yes | Yes | P3 10021185 | 638 | 70 | P01 | 082 - Bowler |  | 80013759 | F | 1-6F-12 1-6F-12 1-6F-12 1-6F-12 1-6F-12 1-6F-10 | Qty <=6 |  | P | 1-6F-12 1-6F-12 1-6F-12 1-6F-12 1-6F-12 1-6F-10
19 |  |  |  | Single material - Single size |  | Yes | Yes | P2 10021186 | 612 | 72 | P01 | 083 - Trapper (Fashion) |  | 80013760 | B | 1-6B-18 1-6B-18 1-6B-18 1-6B-18 | Qty <=6 |  | P | 1-6B-18 1-6B-18 1-6B-18 1-6B-18
20 |  |  |  | Single material - Multiple size |  | Yes | Yes | P6 10021183 | 638 612 658 | 12 22 30 | P01 | 385 - Molded bucket |  | 80013761 | A | 1-6A-8 1-3A-4 1-6A-8 1-6A-8 1-6A-6 1-6A-8 1-6A-8 1-6A-8 1-6A-6 | Qty <=8 |  | P | 1-6A-8 1-3A-4 1-6A-8 1-6A-8 1-6A-6 1-6A-8 1-6A-8 1-6A-8 1-6A-6
21 |  |  |  | Multiple material - Multiple size |  | Yes | Yes | P3+P9 10021175 10021176 | 638 612 658 638 612 658 | 30 24 52 10 15 12 | P01 | 372 - Visor Ballmarker |  | 80013762 | A | 1-6A-24 1-2A-6 1-6A-24 1-6A-24 1-6A-24 1-1A-4 1-6A-8 1-2A-2 1-6A-8 1-6A-7 1-6A-8 1-3A-4 |  |  | P | 1-6A-24 1-2A-6 1-6A-24 1-6A-24 1-6A-24 1-1A-4 1-6A-8 1-2A-2 1-6A-8 1-6A-7 1-6A-8 1-3A-4
22 |  |  |  | Multiple material - Multiple size |  | Yes | Yes | P10+P20 10021173 10021174 | 638 612 658 638 612 658 | 15 10 12 6 10 7 | P01 | 369 - 9Forty |  | 80013763 | B | 1-6B-7 1-6B-7 1-1B-1 1-6B-7 1-3B-3 1-6B-7 1-6B-5 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-2B-1 1-6B-3 1-6B-3 1-2B-1 |  |  | P | 1-6B-7 1-6B-7 1-1B-1 1-6B-7 1-3B-3 1-6B-7 1-6B-5 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-2B-1 1-6B-3 1-6B-3 1-2B-1
Multiple silhouettes, one series |  | No Crossdock, Max Box Size | Pack by SKU |  | Yes | Yes
23 |  |  |  | Multiple material - Single size | Yes | Yes |  | 10020927 10020929 | 638 638 | 55 29 | P01, P06 | 021 - 59Fifty 036 - 59Fifty low crown |  | 80013734 | A | 1-6A-55 1-3A-29 |  |  | P | 1-6A-55 1-3A-29
24 |  |  |  | Multiple material - Multiple size | Yes | Yes |  | 10020932 10020933 10020934 | 638 612 658 638 612 658 638 612 658 | 24 36 42 63 70 40 25 26 70 | P01, P03 | 103 - 9Forty 109 - 59Fifty dogear 116 - 39Thirty downflap |  | 80013735 | B | 1-2B-24 1-2B-24 1-1B-12 1-2B-24 1-2B-18 1-2B-12 1-2B-12 1-2B-12 1-2B-12 1-2B-12 1-1S-3 1-2B-12 1-2B-12 1-2B-12 1-2B-12 1-2B-12 1-2B-10 1-2B-12 1-2B-12 1-2B-12 1-1B-4 1-2B-16 1-2B-9 1-2B-16 1-2B-10 1-2B-16 1-2B-16 1-2B-16 1-2B-16 1-1B-6 | Qty <=6 (PH4-109) Qty<=8 (PH4-116) |  | P | 1-2B-24 1-2B-24 1-1B-12 1-2B-24 1-2B-18 1-2B-12 1-2B-12 1-2B-12 1-2B-12 1-2B-12 1-1S-3 1-2B-12 1-2B-12 1-2B-12 1-2B-12 1-2B-12 1-2B-10 1-2B-12 1-2B-12 1-2B-12 1-1B-4 1-2B-16 1-2B-9 1-2B-16 1-2B-10 1-2B-16 1-2B-16 1-2B-16 1-2B-16 1-1B-6
|  |  |  | Multiple material - Multiple size | Yes | Yes |  | 10020932 10020933 10020934 | 638 612 658 638 612 658 638 612 658 | 100 70 60 225 300 100 70 60 50 | P01,P06 P01,P94 P01,P04 | 103 - 9Forty 109 - 59Fifty dogear 116 - 39Thirty downflap |  | 80013786 | B | 1-4B-48 1-4B-48 1-1B-4 1-4B-48 1-2B-22 1-4B-48 1-1B-12 1-12B-72 1-12B-72 1-12B-72 1-2B-9 1-12B-72 1-12B-72 1-12B-72 1-12B-72 1-2B-12 1-12B-72 1-6B-28 1-3B-24 1-3B-24 1-3B-22 1-3B-24 1-3B-24 1-2B-12 1-3B-24 1-3B-24 1-1S-2 | Qty <=6 (PH4-109) Qty<=8 (PH4-116) |  | P | 1-4B-48 1-4B-48 1-1B-4 1-4B-48 1-2B-22 1-4B-48 1-1B-12 1-12B-72 1-12B-72 1-12B-72 1-2B-9 1-12B-72 1-12B-72 1-12B-72 1-12B-72 1-2B-12 1-12B-72 1-6B-28 1-3B-24 1-3B-24 1-3B-22 1-3B-24 1-3B-24 1-2B-12 1-3B-24 1-3B-24 1-1S-2
Multiple silhouettes, one series |  | No Crossdock, Max Box Size | Pack by SKU |  | Yes | Yes | Yes
80013736
[8 empty] | P3+P2 10021175 10021186 | 80013737
P9+P2 10021176 10021186
80013738
[8 empty] | 10020932 10020943 | 80013739
25 |  |  |  | Multiple material - Single size | Yes | Yes | Yes | P10+P2 10021173 10021186 | 638 638 | 30 24 | P01, P05 | 369 - 9Forty 083 - Trapper (Fashion) |  | 80013764 | B | 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-3 1-1B-3 1-1B-3 1-1B-3 1-1B-3 1-1B-3 1-1B-3 1-1B-3 |  |  | P | 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-1 1-1B-3 1-1B-3 1-1B-3 1-1B-3 1-1B-3 1-1B-3 1-1B-3 1-1B-3
26 |  |  |  | Multiple material - Multiple size | Yes | Yes | Yes | P2+P20 10021186 10021174 | 638 612 658 638 612 658 | 8 16 12 90 120 80 | P01, P06 | 083 - Trapper (Fashion) 369 - 9Forty |  | 80013765 | B | 1-3B-8 1-6B-16 1-4B-12 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-4B-2 |  |  | P | 1-3B-8 1-6B-16 1-4B-12 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-4B-2
27 |  |  |  | Multiple material - Multiple size | Yes | Yes | Yes | P2+P20 10021186 10021174 | 638 612 658 638 612 658 | 60 75 120 40 15 30 | P01,P04 P01,P94 | 083 - Trapper (Fashion) 369 - 9Forty |  | 80013790 | B | 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-2B-6 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-1B-3 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-1B-3 1-12B-7 1-12B-7 1-12B-7 1-12B-7 1-12B-7 1-12B-5 1-12B-7 1-12B-7 1-2B-1 1-12B-7 1-12B-7 1-12B-7 1-12B-7 1-4B-2 |  |  | P | 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-2B-6 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-1B-3 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-3B-9 1-1B-3 1-12B-7 1-12B-7 1-12B-7 1-12B-7 1-12B-7 1-12B-5 1-12B-7 1-12B-7 1-2B-1 1-12B-7 1-12B-7 1-12B-7 1-12B-7 1-4B-2
Multiple silhouettes, one series |  | No Crossdock, No Max Box Size | Pack by SKU |  |  | Yes
28 |  |  |  | Multiple material - Single size |  | Yes |  | 10020932 10020933 | 612 612 | 120 220 | P01 | 103 - 9Forty 109 - 59Fifty dogear |  | 80013738 | B | 1-6B-72 1-4B-48 1-6B-36 1-6B-36 1-6B-36 1-6B-36 1-6B-36 1-6B-36 1-1B-4 |  |  | P | 1-6B-72 1-4B-48 1-6B-36 1-6B-36 1-6B-36 1-6B-36 1-6B-36 1-6B-36 1-1B-4
29 |  |  |  | Multiple material - Multiple size |  | Yes |  | 10020932 10020933 | 638 612 658 638 612 658 | 95 110 62 63 44 79 | P01 | 103 - 9Forty 109 - 59Fifty dogear |  | 80013739 | B | 1-6B-72 1-2B-23 1-6B-72 1-4B-38 1-6B-62 1-6B-36 1-6B-27 1-6B-36 1-2B-8 1-6B-36 1-6B-36 1-2B-7 |  |  | P | 1-6B-72 1-2B-23 1-6B-72 1-4B-38 1-6B-62 1-6B-36 1-6B-27 1-6B-36 1-2B-8 1-6B-36 1-6B-36 1-2B-7
Multiple silhouettes, one series |  | No Crossdock, No Max Box Size | Pack by SKU |  |  | Yes | Yes
80013744
80013745
80013746
80013730
30 |  |  |  | Multiple material - Single size |  | Yes | Yes | P10+P2 10021173 10021186 | 638 638 | 100 25 | P01 | 369 - 9Forty 083 - Trapper (Fashion) |  | 80013766 | B | 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-2B-2 1-6B-18 1-3B-7 |  |  | P | 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-6B-7 1-2B-2 1-6B-18 1-3B-7
31 |  |  |  | Multiple material - Multiple size |  | Yes | Yes | P2+P20 10021186 10021174 | 638 612 658 638 612 658 | 35 12 24 15 12 20 | P01 | 083 - Trapper (Fashion) 369 - 9Forty |  | 80013779 | B | 1-6B-18 1-6B-17 1-4B-12 1-6B-18 1-2B-6 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-4B-2 |  |  | P | 1-6B-18 1-6B-17 1-4B-12 1-6B-18 1-2B-6 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-6B-3 1-4B-2
Multiple silhouettes, multiple series |  | No Crossdock, Max Box Size | Pack by SKU |  | Yes | Yes
32 |  |  |  | Multiple material - Single size | Yes | Yes |  | 10020932 10020943 | 638 638 | 123 160 | P01, P03 | 103 - 9Forty 373 - Stretch bucket |  | 80013742 | A,S | 1-2B-24 1-2B-24 1-2B-24 1-2B-24 1-2B-24 1-1S-3 1-2A-16 1-2A-16 1-2A-16 1-2A-16 1-2A-16 1-2A-16 1-2A-16 1-2A-16 1-2A-16 1-2A-16 |  |  | P | 1-2B-24 1-2B-24 1-2B-24 1-2B-24 1-2B-24 1-1S-3 1-2A-16 1-2A-16 1-2A-16 1-2A-16 1-2A-16 1-2A-16 1-2A-16 1-2A-16 1-2A-16 1-2A-16
33 |  |  |  | Multiple material - Multiple size | Yes | Yes |  | 10020933 10020943 | 638 612 658 638 612 658 | 56 40 23 72 160 40 | P01, P06 | 109 - 59Fifty dogear 373 - Stretch bucket |  | 80013751 | A , B | 1-6B-36 1-4B-20 1-6B-36 1-1B-4 1-4B-23 1-6A-48 1-3A-24 1-6A-48 1-6A-48 1-6A-48 1-2A-16 1-6A-40 |  |  | P | 1-6B-36 1-4B-20 1-6B-36 1-1B-4 1-4B-23 1-6A-48 1-3A-24 1-6A-48 1-6A-48 1-6A-48 1-2A-16 1-6A-40
34 |  |  |  | Multiple material - Multiple size | Yes | Yes |  | 10020933 10020943 | 638 612 658 638 612 658 | 40 50 60 200 150 300 | P01, P06 P01,P94 | 109 - 59Fifty dogear 373 - Stretch bucket |  | 80013787 | A , B | 1-4B-24 1-3B-16 1-4B-24 1-4B-24 1-1S-2 1-4B-24 1-4B-24 1-2B-12 1-12A-96 1-12A-96 1-1A-8 1-12A-96 1-12A-54 1-12A-96 1-12A-96 1-12A-96 1-2A-12 |  |  | P | 1-4B-24 1-3B-16 1-4B-24 1-4B-24 1-1S-2 1-4B-24 1-4B-24 1-2B-12 1-12A-96 1-12A-96 1-1A-8 1-12A-96 1-12A-54 1-12A-96 1-12A-96 1-12A-96 1-2A-12
Multiple silhouettes, multiple series |  | No Crossdock, Max Box Size | Pack by SKU |  | Yes | Yes | Yes
35 |  |  |  | Multiple material - Single size | Yes | Yes | Yes | P3+P2 10021175 10021186 | 638 638 | 25 20 | P01, P04 | 372 - Visor Ballmarker 083 - Trapper (Fashion) |  | 80013768 | A , B , S | 1-3A-12 1-3A-12 1-1S-1 1-3B-9 1-3B-9 1-1B-2 |  |  | P | 1-3A-12 1-3A-12 1-1S-1 1-3B-9 1-3B-9 1-1B-2
36 |  |  |  | Multiple material - Multiple size | Yes | Yes | Yes | P9+P2 10021176 10021186 | 638 612 658 638 612 658 | 108 220 120 36 30 50 | P01, P94 | 372 - Visor Ballmarker 083 - Trapper (Fashion) |  | 80013769 | A,B | 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-12 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-12 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-6A-8 1-12B-36 1-12B-30 1-12B-36 1-6B-14 |  |  | P | 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-12 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-12 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-12A-16 1-6A-8 1-12B-36 1-12B-30 1-12B-36 1-6B-14
|  |  |  | Multiple material - Multiple size | Yes | Yes | Yes | P9+P2 10021176 10021186 | 638 612 658 638 612 658 | 30 40 50 50 70 100 | P01,P03 P01,P06 | 372 - Visor Ballmarker 083 - Trapper (Fashion) |  | 80013788 | A,B | 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-4B-12 1-4B-12 1-4B-12 1-4B-12 1-1B-2 1-4B-12 1-4B-12 1-4B-12 1-4B-12 1-4B-12 1-4B-10 1-4B-12 1-4B-12 1-4B-12 1-4B-12 1-4B-12 1-4B-12 1-4B-12 1-4B-12 1-2B-4 |  |  | P | 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-2A-2 1-4B-12 1-4B-12 1-4B-12 1-4B-12 1-1B-2 1-4B-12 1-4B-12 1-4B-12 1-4B-12 1-4B-12 1-4B-10 1-4B-12 1-4B-12 1-4B-12 1-4B-12 1-4B-12 1-4B-12 1-4B-12 1-4B-12 1-2B-4
Multiple silhouettes, multiple series |  | No Crossdock, No Max Box Size | Pack by SKU |  |  | Yes
37 |  |  |  | Multiple material - Single size |  | Yes |  | 10020932 10020943 | 638 612 | 136 115 | P01 | 103 - 9Forty 373 - Stretch bucket |  | 80013746 | A,B | 1-6B-72 1-6B-64 1-6A-48 1-6A-48 1-3A-19 |  |  | P | 1-6B-72 1-6B-64 1-6A-48 1-6A-48 1-3A-19
38 |  |  |  | Multiple material - Multiple size |  | Yes |  | 10020933 10020943 | 638 612 658 638 612 658 | 69 40 80 70 60 50 | P01 | 109 - 59Fifty dogear 373 - Stretch bucket |  | 80013753 | A,B | 1-6B-36 1-6B-33 1-6B-36 1-1B-4 1-6B-36 1-6B-36 1-2B-8 1-6A-70 1-6A-60 1-6A-50 |  |  | P | 1-6B-36 1-6B-33 1-6B-36 1-1B-4 1-6B-36 1-6B-36 1-2B-8 1-6A-70 1-6A-60 1-6A-50
Multiple silhouettes, multiple series |  | No Crossdock, No Max Box Size | Pack by SKU |  |  | Yes | Yes
39 |  |  |  | Multiple material - Single size |  | Yes | Yes | P3+P2 10021175 10021186 | 638 638 | 40 50 | P01 | 372 - Visor Ballmarker 083 - Trapper (Fashion) |  | 80013770 | A,B | 1-6A-24 1-4A-16 1-6B-18 1-6B-18 1-6B-14 |  |  | P | 1-6A-24 1-4A-16 1-6B-18 1-6B-18 1-6B-14
40 |  |  |  | Multiple material - Multiple size |  | Yes | Yes | P3+P2 10021175 10021186 | 638 612 658 638 612 658 | 20 30 40 25 30 45 | P01 | 372 - Visor Ballmarker 083 - Trapper (Fashion) |  | 80013771 | A,B | 1-6A-20 1-6A-24 1-2A-6 1-6A-24 1-4A-16 1-6B-18 1-3B-7 1-6B-18 1-4B-12 1-6B-18 1-6B-18 1-3B-9 |  |  | P | 1-6A-20 1-6A-24 1-2A-6 1-6A-24 1-4A-16 1-6B-18 1-3B-7 1-6B-18 1-4B-12 1-6B-18 1-6B-18 1-3B-9

## Error Logs
S.No | Scenario | Error log
Outbound
1 | Multiple VAS codes(Max boxes / pack types) for a material in the delivery | Packing not possible due to multiple VAS codes.
2 | Try packing already packed delivery | Packing or PGI is already done for the delivery
3 | ZCD/ZCL - without run size ratios | Incorrect run size
4 | ZCD/ZCL - Mismatch of quantities to run size ratio | Incorrect run size and quantity
5 | ZCD/ZCL - Run size ratio is more than 12 | Maintain valid run size ratio <= 12
6 | Quantity split for a particular size in delivery | Packing not possible due to quantity split
7 | Missing of packaging material for the Box series | Packaging material not found for box series *
8 | Missing UPC's for the materials in the delivery | Packing not possible due to missing UPC's in delivery
9 | Invalid delivery number as input in selection screen | No relevant deliveries/data found for Packing
10 | ZCL/ZCD missing but run size maintained | Missing usage indicator
11 | PH4 missing | PH4 not maintained *
12 | Invalid shipping point | Invalid shipping point
13 | Pack a return delivery | Delivery not relevant for packing
Inbound
1 | * PO type without ZSNC confirmation | Delivery not relevant for packing

## Sheet1
7B error | 80013749 | Packaging material not found for box series *7B