## OPPM
|  |  |  | Project Leader: | Rahul Attarde/Kris Paxson | [5 empty] | Project: |  |  | SAP WM IMPLEMENTATION - HONG KONG
|  |  |  | Objective: | Enable and implement SAP Warehouse Management in New Era, and deploy to Hong Kong DC
Objectives |  |  |  |  | Major Tasks | Status | Schedule | [21 empty] | RACI | [13 empty] | Artifact
O |  |  |  |  | Project Preparation and Kick Off
O | O | O |  |  | Requirements Gathering | [23 empty] | R | R | C | C | C | I | C | A | C | C | I | I | ™
O | O | O |  |  | Project Definition and Kick Off | [23 empty] | R | R | C | C | C | I | C | A | C | C | I | I | ˜ |  | Project Scope Definition and Project Kick Off Documentation
O | O |  |  |  | Process and Solution Design and Finalization | bar: R R to R R; A A to C C
O | O |  |  |  | Process Definition | [23 empty] | R R: R; R R: R; C C: C; C C: A |  |  | Process Flow Diagram or SOP
| O | O | O |  | Solution Definition | [37 empty] | Build Templates (Configuration Values), Org Structure (WH Structure), RICEF Design Spec, Report Definition, Test Plan | bar: R R to R R; A A
O | O |  | O |  | Data Migration Strategy (Data Source, Transformation, Loading) | [37 empty] | Data Migration Plan and Process, Data Transformation/Load Document | bar: R R to R R
O | O | O | O |  | Project Build Phase
O | O | O | O |  | System Build - Configuration and Development | [23 empty] | R R: A; R R: C; C C: C; C C: C; C C: R; I I: R; I I: R |  |  | Unit Test Scripts
|  | O |  |  | System Build - Business Intelligence | [23 empty] | A | C | C | C | C | C | I | I | I | R | R | R |  |  | Unit Test Scripts
O |  |  | O |  | System Build - Data Conversion Tools | [23 empty] | A: A; C: C; C: C; I: R; R: R; R: R; R: R |  |  | Unit Test Scripts
O | O |  |  |  | Integration Testing 1 (US) | [37 empty] | Integration Test Scripts/Panaya, Summary Metrics | bar: A to C; R to R
O | O |  |  |  | Integration Testing 2 (US) | [37 empty] | Integration Test Scripts/Panaya, Summary Metrics | bar: A to C; R to R
O | O | O |  |  | Integration Testing 3 (Both US and HK Test Locations) | [23 empty] | A | R | R | R | R | R | R | I | I | A | R | R |  |  | Integration Test Scripts/Panaya, Summary Metrics
O | O |  | O |  | Data Migration - Initial Extraction of SIMMS Data | [23 empty] | R | A | C | C |  | R | R | I | I | R | R | R |  |  | Extract and Load Files
O | O |  | O |  | Data Migration - Second Extraction and Conversion of SIMMS Data | [23 empty] | R | A | C | C |  | R | R | I | I | R | R | R | ™ |  | Extract and Load Files
O | O |  | O |  | Data Migration - Cutover Rehearsal and Cycle 3 Data Preparation | [23 empty] | R | A | C | C |  | R | R | I | I | [5 empty] | Extract, Load and Validation Files
| O |  | O |  | Training Preparation - Documentation and eLearning | [23 empty] | A: A; C: A; C: R; I: C; R: R | ▲ | ▲ | Training Plan, Training Documents, uPerform Recordings
Final Preparation For Go-Live
| O |  | O |  | Training Execution - Train the Trainer | [35 empty] | ˜ | ● | bar: A to C; C to I; R
| O |  | O |  | Training Execution - End User Training | [37 empty] | Session Rosters/Trackers/Feedback | bar: A to C; C to I; R
O | O |  |  |  | Site Preparation - Inventory Accuracy Validation and CleanUp | bar: C; C to I
O | O |  |  |  | Site Preparation - Reorganization/Bin Labeling | [37 empty] | Final Org/WH Structure Document | bar: C; C to I
O | O |  |  |  | Site Preparation - Final Inventory Cycle Count/Location Validation | [35 empty] | ▼ | ▼ | bar: C; C to I
O | O |  |  |  | Cutover - Extract SIMMS Location Data and load to SAP | [37 empty] | Extract, Load and Validation Files | bar: A; C to I; R to R
O | O |  |  |  | Cutover - Replace In-Process Paperwork in Warehouse | bar: A; C to I; R
O | O |  |  |  | Go-Live and Support | [36 empty] | 1 | bar: A to C; C to I; R to R
O | O |  | O |  | Onsite Stabilization | [35 empty] | ▲ | bar: A; C to I; R
O | O |  | O |  | Remote Stabilization | [35 empty] | ˜ | bar: A to C; R to R
|  |  | O |  | Project Closure | [35 empty] | ▼ | bar: A to C; I to I
Communication Plan - Events
Kick Off Session (1/29) | bar: A to C
Design Finalization (2/8) | bar: A to C
System and Process Walkthrough (3/6) | bar: A to C
Training and Cutover Launch (3/18) | bar: A to C
[5 empty] | Executive Go-NoGo Decision (3/29) | [37 empty] | Executive Summary for Go-NoGo (Test/Training/Site Readiness Completion Summary) | bar: A to C; I to I
[5 empty] | US Team Members On Location in HK (IT & Functional) | [9 empty] | Ken |  |  | Rahul/Kris
[5 empty] | US Team Members On Location in HK (IT & Functional) | [10 empty] | TBD/TBD
Enable Integrated In-House WM Solution | Enable Instructed Picking, Putaway, "Cycle Counting" Processes | Provide Key Operational Reports | Provide Scalable Solution for easy deployment |  | ▲ Tracking on schedule |  | 2013-01-14 | 2013-01-21 | 2013-01-28 | 2013-02-04 | 2013-02-11 | 2013-02-18 | 2013-02-25 | 2013-03-04 | 2013-03-11 | 2013-03-18 | 2013-03-25 | 2013-04-01 | 2013-04-08 | 2013-04-15 | 2013-04-22 | 2013-04-29 | 2013-05-06 | 2013-05-13 | 2013-05-20 | 2013-05-27 | 2013-06-03 | 2013-06-10 | Rahul Attarde | Kris Paxson | Jennifer Wolf | Doug Snyder | Robin Hahn | Sonia Chu | Menlo WMS Resource | Ken Berg | David Velasquez | Poter Wong | BMS | IT Team
˜ May need attention
▼ Behind schedule or negative impact
[R]esponsible (completes work)
[A]ccountable (answers for the work completed)
[C]onsulted (opinions are sought from; SME's)
[I]nformed (kept up to date)
Team
[5 empty] | 1) Rahul Attarde | 8) Ken Berg | 2013-01-14: 8) Menlo WMS Resource (Menlo HK Ops Manager until staffed)
[5 empty] | 2) Kris Paxson | 9) Poter Wong | 2013-01-14: 9) Ken Berg
[5 empty] | 3) Jennifer Wolf | 10) Menlo WMS Resource | 2013-01-14: 10) David Velasquez
[5 empty] | 4) Doug Snyder | 11) BMS | 2013-01-14: 11) Poter Wong
[5 empty] | 5) Robin Hahn | 12) IT Functional Team | 2013-01-14: 12) BMS
[5 empty] | 7) Sonia Chu |  | 2013-01-14: 13) IT Team

## OPPM_Old
[5 empty] | Project Leader: | Rahul Attarde/Kris Paxton | [5 empty] | Project: |  |  | SAP WM IMPLEMENTATION - HONG KONG
[5 empty] | Objective: | Enable and implement SAP Warehouse Management in Hong Kong DC
Objectives | [5 empty] | Major Tasks | Status | Schedule | [21 empty] | RACI
|  |  |  | O |  | Gather Requirements | [23 empty] | A | C |  |  | C | C |  | R |  | C
|  |  |  | O |  | Agreement on Scope - Project Definition | [23 empty] | A | C |  |  | C | C |  |  |  | C |  |  | ™
|  |  |  | O |  | Project Kick-off | [23 empty] | A | [6 empty] | R |  |  |  |  | ˜
Process and Solution Finalization (Blueprint Design)
O | O | O |  |  |  | SAP Configuration and Development | [23 empty] | R |  | A | [8 empty] | A
O | [5 empty] | SAP configuration - Organization Setup | [23 empty] | R | [10 empty] | A
| O |  |  |  |  | SAP configuration - Put-away | [23 empty] | R | [10 empty] | A
| O |  |  |  |  | SAP configuration - Picking | [23 empty] | R | [10 empty] | A
| O |  |  |  |  | SAP configuration - Inventory transactions | [23 empty] | R | [10 empty] | A
|  |  | O |  |  | Conversion Program and/or Script Development | [23 empty] | R | [10 empty] | A
|  |  | O |  |  | BI Report Development | [23 empty] | R | C |  | A | C |  |  |  |  | C |  | A
|  |  |  | O |  | Integration Testing 1 - Mock Data | [23 empty] | R |  | A | A
|  |  |  | O |  | Integration Testing 2 - Sample Conversion Data | [23 empty] | R |  | A | A | [8 empty] | ™
|  |  | O | O |  | Cutover Simulation - IT3 Data Preparation | [23 empty] | R |  |  | A | [7 empty] | A
|  |  |  | O |  | Integration Testing 3 - Converted Data | [23 empty] | R | A | A | A | A | A | A |  | A | A |  |  | ▲ | ▲
|  |  | O | O |  | Training Preparation and Execution | [35 empty] | ˜ | ●
|  |  | O | O |  | Training Documentation and eLearing Preparation | [23 empty] | A | R | [6 empty] | A | C
|  |  | O | O |  | Training Execution | [23 empty] | A | R | [6 empty] | A | A
O | O |  |  |  |  | Pre go-live Site preparation | [23 empty] | C | R | [6 empty] | A | A |  |  | ▼ | ▼
O | O |  |  |  |  | Restructure/Reorganize DC/Finalize Bin Labeling | [23 empty] | C | R | [6 empty] | A | A
O | O |  |  | O |  | Physical Inventory Count | [23 empty] | C | R | [6 empty] | A | A
O | O |  |  | O |  | Cut-over activities - Inventory transfer from SIMMS to SAP | [23 empty] | R | A |  |  |  | A | A |  | A | A |  | A |  | 1
O | O |  |  |  |  | Go-Live | [23 empty] | R | A | [6 empty] | A | A |  | A | ▲
O | O | O |  |  |  | Post go-live support | [23 empty] | R | A |  |  | C | C | C |  | A | A |  | C | ˜
|  |  |  | O |  | Project Close out | [23 empty] | A | [6 empty] | R |  |  |  |  | ▼
Communication Plan
Kick Off Session
System and Process Walkthrough
Training and Cutover Launch
Executive Go-NoGo Decision
Enable Integrated In-House WM Solution | Enable Instructed Picking, Putaway, "Cycle Counting" Processes | Provide Key Operational Reports | Provide Scalable Solution for easy deployment |  |  | ▲ Tracking on schedule |  | 2013-01-14 | 2013-01-21 | 2013-01-28 | 2013-02-04 | 2013-02-11 | 2013-02-18 | 2013-02-25 | 2013-03-04 | 2013-03-11 | 2013-03-18 | 2013-03-25 | 2013-04-01 | 2013-04-08 | 2013-04-15 | 2013-04-22 | 2013-04-29 | 2013-05-06 | 2013-05-13 | 2013-05-20 | 2013-05-27 | 2013-06-03 | 2013-06-10 | Rahul Attarde | Kris Paxson | Dan Brennan | Babu Lankipalli | Jen Wolf | Doug Snyder | Robin Hahn | Ken Berg | Poter Wong | Menlo WMS Resource | Baiwa Zhang | BMS
˜ May need attention
▼ Behind schedule or negative impact
[R]esponsible (completes work)
[A]ccountable (answers for the work completed)
[C]onsulted (opinions are sought from; SME's)
[I]nformed (kept up to date)
Team
[6 empty] | 1) Rahul Attarde | 7) Chris Kraft / Robin Hahn
[6 empty] | 2) Kris Paxson | 8) Ken Berg
[6 empty] | 3) Thi Tran / Dan Brennan | 9) Poter Wong
[6 empty] | 4) Babu Lankipalli / Baiwa Zhang | 10) Menlo WMS Resource
5) Jen Wolf / Jill Ross
6) Doug Snyder / Mike Spiker