## Sheet1
S. No. | Factory | Date | PO# | Issue in Detail | Me on 02/17/2015 | Poter Reply on 02/18/2015 | On 02/18/2015
1 | ML | 2015-02-17 | 4500113875 | Inbound Delivery Missing after SEW, I couldn’t find ZN confirmation in ECC, could you help to check any IDoc failed? | Need some time to analyse please. | Jeff found item 350 is not compete SEW, I am asking factory to update.
2 | EB | 2015-02-16 | 4500117723 | “Actual Data” line missing in Work Order Worklist on item no. 80/90/110/120/140/150/180/220/270/290/310/360/400/420/430/450/470/480/570/600/610/640/ | As a work around, we can give the work orders as input in the program ZNEC_WO_WL_CREATE and run which shall create the work lists for all the work orders. | I executed ZNEC_WO_WL_CREATE, but Actual Data lines still missing in Work Order Worklist 660/680/690/700/710/740/750/760/790/820/830/860/880/890/940/960/690/1080/1100/1200/1210/1250/1350/1370/1390/1410/1460/1520/1540/1600/1650/1660/1700/1740/1760/1790/1800/1820/18501880/1960/1970/1990/2000/2020/2040/2080/2090/2100/2140 I tried to run ZNEC_WO_WL_CREATE, but still not showing | SOLVED Work Lists are created, I have created a variant and Jeff has ran the program which has created the Work Lists.
3 | EB | 2015-02-16 | 4500122267 | Inbound Delivery Missing after SEW, I couldn’t find ZN confirmation in item 500, could you help to check any IDoc failed? | Yes IDOC is failed (Please see below item 2) | Who can fix the IDOCS? | The New IDOC is processed with correct data and ZN is updated. INB Delivery is yet to be created by program
4 | EB | 2015-02-16 | 4500122266 | Inbound Delivery Missing after SEW | IDOCS which updates the confirmation failed due to wrong data in the IDOC (Please see below item 3) | Who can fix the IDOCS? | The New IDOC is processed with correct data and ZN is updated, INB Delivery is yet to be created by program
5 | EB | 2015-02-16 | 4500121774 | Inbound Delivery Missing after SEW | Confirmations were not updated form SNC as the Work Order Work List is not created. (Please see below item 4) | I executed ZNEC_WO_WL_CREATE, but Actual Data lines still missing in Work Order Worklist | Work Lists created for lines 20, 90 , 100 & 180 of PO 4500121774. Please have EB to update the Confirmations which shall be updated in the ECC PO. When ZN is updated for all above lines INB Delivery would be created.
6 | EB | 2015-02-16 | 4500121446 | Unable to publish ASN under this PO: | I am not aware of this | Attached the error message, you can try to publish those ASN | Assuming this is caused by missing ship to adress.